## Development 7.5.11 Gantt Chart
PROJECT: VERSION 7.5.11
Nutec Infotech Pvt Ltd | [5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Development Team
Project start date: | 2023-07-19 | [5 empty] | July | [13 empty] | August | [34 empty] | September
Scrolling increment: | 0 | time axis 2023-07-19 to 2023-09-12
Milestone description | Category | Progress | Start | Remarks | Bug Id | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
SPRINT - 1(July Fourth Week 18 July to 21 July)
ICE MAKE-In sales order if we select payment terms and in invoice payment terms is different then net sales amount differnce is coming in the form. | Milestone | 100% | 2023-07-19 | Completed | 20220721-003 | 3 | bar: W to F
C Suma bhai-Print document working while save the sales invoice. | Milestone | 100% | 2023-07-19 | Completed |  | 3 | bar: W to F
C Suma bhai-Sales Invoice generate through Mobile App( Final point is pending salesinvoicefinancedetails and salesinvoice header table is wrong) | High Risk | 70% | 2023-07-19 | Return | 20221003-001 | 3
C Suma bhai-Branch Receipt pending list comes and save in the system. | High Risk | 60% | 2023-07-19 | Return |  | 3
Additional Task Covered
Prasad-without selecting manufacturing indent check box and also system not validate and allow to save forecast document | Milestone | 100% | 2023-07-19 | Completed | 20230523-002 | 3 | bar: W to F
Highcool-Add multiple items add in forecast | Milestone | 100% | 2023-07-19 | Completed | 20233105-003 | 3 | bar: W to F
Prasad-if forecast document save without selecting manufacturing indent check box then if we edit/amend same forecast document and select the manufacturing indent check box then system allow to select and save the document | Milestone | 100% | 2023-07-19 | Completed | 20230523-002 | 3 | bar: W to F
SPRINT - 2(July Fifth Week 24 July to 28 July)
Prasad-without selecting manufacturing indent check box and also system not validate and allow to save forecast document | Milestone | 100% | 2023-07-24 | Return(It comes from last sprint) |  | 5 | bar: M to F
Prasad - When we set authorization on purchase order cancellation category and do the pruchase order cancellation against po then system does not allow to edit/amend.cancel po document untill and unless its authorized. | Milestone | 100% | 2023-07-24 |  |  | 5 | bar: M to F
C Suma bhai-Sales Invoice generate through Mobile App( Final point is pending salesinvoicefinancedetails and salesinvoice header table is wrong) | Goal | 70% | 2023-07-24 |  |  | 5 | M: 2; T: 2; W: 2; T: 2; F: 2
Alps - When we do the Holiday setup for all the emplyee and If any Employee comes on holiday then while impoting data from SQL Present (P) should be applicable for that employe on respective holiday. | Goal | 0% | 2023-07-24 |  |  | 5 | M: 2; T: 2; W: 2; T: 2; F: 2
Prakash - when we are generate payroll conformation that time half day is not consider in present day . | Goal | 0% | 2023-07-24 |  | 20230228-002 | 5 | M: 2; T: 2; W: 2; T: 2; F: 2
Prakash - Item Amount Calculate wrong in process receipt form | Goal | 0% | 2023-07-24 |  | 20200916-004 | 5 | M: 2; T: 2; W: 2; T: 2; F: 2
Aeron - Holiday shift should not counted in the Process Schedule form. | Goal | 0% | 2023-07-24 |  |  | 5 | M: 2; T: 2; W: 2; T: 2; F: 2
Aeron - Process scheculer same date will not consider in that form | Goal | 0% | 2023-07-24 |  |  | 5 | M: 2; T: 2; W: 2; T: 2; F: 2
C Suma bhai-Branch Receipt pending list comes and save in the system. | Goal | 50% | 2023-07-24 |  |  | 5 | M: 2; T: 2; W: 2; T: 2; F: 2
SPRINT - 3(August First Week 01 Aug to 4 August)
C Suma bhai-Sales Invoice generate through Mobile App( Final point is pending salesinvoicefinancedetails and salesinvoice header table is wrong) | Goal | 90% | 2023-08-01 |  |  | 4
C Suma bhai-Branch Receipt pending list comes and save in the system. | Goal | 90% | 2023-08-01
Alps - When we do the Holiday setup for all the emplyee and If any Employee comes on holiday then while impoting data from SQL Present (P) should be applicable for that employe on respective holiday. | Goal | 0% | 2023-08-01 | Shit to next sprint due to suma bhai work
Prakash - when we are generate payroll conformation that time half day is not consider in present day . | Goal | 0% | 2023-08-01 | Shit to next sprint due to suma bhai work
Prakash - Item Amount Calculate wrong in process receipt form | Goal | 0% | 2023-08-01 | Shit to next sprint due to suma bhai work
Aeron - Holiday shift should not counted in the Process Schedule form. | Goal | 0% | 2023-08-01 | Shit to next sprint due to suma bhai work
Additional Task Done Which is not Planned
Self- Some field value not save in policy table (20191224-001) | Milestone | 100% | 2023-08-03
Self - When we create new document and enter party name after that company,branch,division does not lock. | Milestone | 100% | 2023-08-03
C Suma bhai - Create pdf for branch issue ,branch receipt and sales invoice.(20230804-001) | Milestone | 100% | 2023-08-03
SPRINT - 4(August Second Week 07 Aug to 11 August )
C Suma bhai-Sales Invoice generate through Mobile App( Final point is pending salesinvoicefinancedetails and salesinvoice header table is wrong) | Milestone | 100% | 2023-08-01
C Suma bhai-Branch Receipt pending list comes and save in the system. | Milestone | 100% | 2023-08-01
C Suma bhai - Create generic report API (20230807-001) 1)Analysis reports list of reports service creation 2)Document level reports list service creation. 3)Generic report pdf creation. | Milestone | 100% |  | New Point Comes in Sprint
Alps - When we do the Holiday setup for all the emplyee and If any Employee comes on holiday then while impoting data from SQL Present (P) should be applicable for that employe on respective holiday. | Milestone | 100% |  | Coding Done checkin on Wednesday
Prakash - when we are generate payroll conformation that time half day is not consider in present day . | Goal | 0% |  | Shifted in Fourth Week
Prakash - Item Amount Calculate wrong in process receipt form | Goal | 0% |  | Shifted in Fourth Week
Aeron - Holiday shift should not counted in the Process Schedule form. | Goal | 0% |  | Shifted in Next Sprint
ICE MAKE - 20220201-003 When we create godown issue based on the indent then form will be slow | Goal | 0% |  | Shifted in Fourth Week
SPRINT - 5(August Third Week 14 Aug to 18 August )
Aeron - Holiday shift should not counted in the Process Schedule form. | Goal | 90% | 2023-08-16 | Coding Done in a Return process
SANGIR PLASTICS PVT. LTD.-In Po Case Alternet Unit Use And Grn Delete That Time Pending Not Proper Update In Purchaseorderdetaiilstable | Goal | 0% | 2023-08-16
Additional Task Done Which is not Planned
Aeron - Inida mart api not working | Milestone | 100% |  | We missed in last week so inclued in that week
Company not able to create | Milestone | 100%
SPRINT - 6(August Fourth Week 21 Aug to 25 August )
Prasad- When stock is taken in alternate unit and issue in alternate unit then validation occurred " available quantity is not updated properly. | Goal | 20% |  | InProcess
Aeron - Process scheculer same date will not consider in that form. | Goal | 70% |  | Return
C suma bhai - write log for all forms. | Milestone | 100% |  | Completed
Aeron - Holiday shift should not counted in the Process Schedule form. | Milestone | 100% | 2023-08-16 | Completed
Esperer- After save document not set previous company name ,branch name,division name and cateory on all fomr | Goal | 90% |  | Return
C suma bhai - create a generic reports API (Return) | Milestone | 100% |  | Completed
Additional Task Done Which is not Planned
When we create sales invoice through mobile app then search criterial is not working . | Milestone | 100% |  | Completed
Esperer-Improved the performance in the sales inquiry form. | Milestone | 100% |  | Completed
Fabtech - System showing error while retreiving one document. Day Report form problem. | Milestone | 100% |  | Completed
Fabtech- Solved the fabtech restriction relevant issue online. | Milestone | 100% |  | Completed
SPRINT - 7(August Fourth Week 28 Aug to 1 September )
Aeron - Process scheculer same date will not consider in that form. | Goal | 70% |  | Return
Esperer- After save document not set previous company name ,branch name,division name and cateory on all fomr | Goal | 90% |  | Return
Prasad- When stock is taken in alternate unit and issue in alternate unit then validation occurred " available quantity is not updated properly. | Goal | 20% |  | InProcess
SANGIR PLASTICS PVT. LTD.-In Po Case Alternet Unit Use And Grn Delete That Time Pending Not Proper Update In Purchaseorderdetaiilstable | Goal | 60% |  | InProcess
Ayushakti-While deleting sales invoice pending quantity update wrong in the sales order table . | Goal | 0% |  | InProcess(Planned in the Next Version)
Esperer - In sales order performance relevant issue solved. | Goal | 0% |  | InProcess(Planned in the Next Version)
IceMake - parameter of party account masterid and batch no is not working in complain inward. | Goal | 0% |  | InProcess(Planned in the Next Version)
Self - Returnable Receipt add quantity more than pending quantity and save document that time error message comes . | Goal | 0% |  | InProcess(Planned in the Next Version)
Self - Error message displays when select party name in fixed deposit receipt interest. | Goal | 0% |  | InProcess(Planned in the Next Version)
ReWork/Return Consideration/Urgent Bug Consideration
We consider date from 21 August to 4 September+Plus testing team will done the testing after the week development
Version Released Date On Or Before 05 September (We tried to complete on before that date )
| Goal | 0% |  |  |  | 9
Task 3 | Goal | 0% | 1900-01-04 |  |  | 11

## Testing 7.5.11 Gantt Chart
PROJECT: VERSION 7.5.11
Nutec Infotech Pvt Ltd | [5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Testing Team
Project start date: | 2023-07-19 | [5 empty] | July | [13 empty] | August | [34 empty] | September
Scrolling increment: | 0 | time axis 2023-07-19 to 2023-09-12
Milestone description | Category | Progress | Start | Remarks | Bug Id | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
SPRINT - 1(July Fourth Week 18 July to 21 July)
ICE MAKE-In sales order if we select payment terms and in invoice payment terms is different then net sales amount differnce is coming in the form. | Milestone | 100% | 2023-07-19 | Completed | 20220721-003 | 3 | bar: W to F
C Suma bhai-Print document working while save the sales invoice. | Milestone | 100% | 2023-07-19 | Completed |  | 3 | bar: W to F
C Suma bhai-Sales Invoice generate through Mobile App( Final point is pending salesinvoicefinancedetails and salesinvoice header table is wrong) | High Risk | 70% | 2023-07-19 | Return(Not come from development | 20221003-001 | 3
C Suma bhai-Branch Receipt pending list comes and save in the system. | High Risk | 0% | 2023-07-19 | Not come from development |  | 3
Additional Task Comes and Start the work
All BUGS EXE Testing by testing team.(Version 7.5.10) | Milestone | 100% | 2023-07-19 |  |  | 1 | bar: W
Prasad-without selecting manufacturing indent check box and also system not validate and allow to save forecast document | Milestone | 25% | 2023-07-19 | Additional | 20230523-002 | 3 | bar: W to F
Highcool-Add multiple items add in forecast | Milestone | 25% | 2023-07-19 | Additional | 20233105-003 | 3 | bar: W to F
Prasad-if forecast document save without selecting manufacturing indent check box then if we edit/amend same forecast document and select the manufacturing indent check box then system allow to select and save the document | Milestone | 25% | 2023-07-19 | Additional | 20230523-002 | 3 | bar: W to F
SPRINT - 2(July Fifth Week 24 July to 28 July)
Prasad-without selecting manufacturing indent check box and also system not validate and allow to save forecast document | Milestone | 100% | 2023-07-24 |  |  | 5 | bar: M to F
Highcool-Add multiple items add in forecast | Milestone | 100% | 2023-07-24 |  |  | 5 | bar: M to F
Prasad-if forecast document save without selecting manufacturing indent check box then if we edit/amend same forecast document and select the manufacturing indent check box then system allow to select and save the document | Milestone | 100% | 2023-07-24 |  |  | 5 | bar: M to F
C Suma bhai-Sales Invoice generate through Mobile App( Final point is pending salesinvoicefinancedetails and salesinvoice header table is wrong) | Goal | 70% | 2023-07-24 |  |  | 4 | T: 2
C Suma bhai-Branch Receipt pending list comes and save in the system. | Goal | 50% | 2023-07-24
Additional Task Done Which is not Planned
Prasad - When we set authorization on purchase order cancellation category and do the pruchase order cancellation against po then system does not allow to edit/amend.cancel po document untill and unless its authorized. (20230519-001) | Milestone | 100% | 2023-07-24 |  |  | 5
SPRINT - 3(August First Week 01 Aug to 4 August and 31 July)
C Suma bhai-Sales Invoice generate through Mobile App( Final point is pending salesinvoicefinancedetails and salesinvoice header table is wrong) | Goal | 90%
C Suma bhai-Branch Receipt pending list comes and save in the system. | Goal | 90%
C Suma bhai - In Mobile app should not use in proper connection strin(20230727-001) | Milestone | 100%
Prasad - When we import excel sheet in purchase indent form that time excel sheet duplicate item validations. | Milestone | 100%
When we configure Tax master id in the export with out payment tab after save tick remove automatically. | Milestone | 100%
Additional Task Done Which is not Planned
Self- Some field value not save in policy table (20191224-001) | Milestone | 100%
Self - When we create new document and enter party name after that company,branch,division does not lock. | Milestone | 100%
SPRINT - 4(7 August - 11 August)
C Suma bhai-Sales Invoice generate through Mobile App( Final point is pending salesinvoicefinancedetails and salesinvoice header table is wrong) | Goal | 95% |  | Verify Once By Rangani
C Suma bhai-Branch Receipt pending list comes and save in the system. | Milestone | 100%
C Suma bhai - Create pdf for branch issue ,branch receipt and sales invoice.(20230804-001) | Milestone | 100%
C Suma bhai - Create generic report API (20230807-001) | Goal | 10% |  | Comes on last Thursday
Aeron - Holiday shift should not counted in the Process Schedule form. | Goal | 50% |  | Return comes on last Friday
SPRINT - 5(14 August - 18 August)
C Suma bhai-Sales Invoice generate through Mobile App( Final point is pending salesinvoicefinancedetails and salesinvoice header table is wrong) | Milestone | 100%
C Suma bhai - Create generic report API (20230807-001) | Goal | 90%
Aeron - Holiday shift should not counted in the Process Schedule form. | Goal | 90%
Alps - When we do the Holiday setup for all the emplyee and If any Employee comes on holiday then while impoting data from SQL Present (P) should be applicable for that employe on respective holiday. | Milestone | 100%
Additional Task Done Which is not Planned
Aeron - Inida mart api not working | Milestone | 100% |  | We missed in last week so inclued in that week
SPRINT - 6(August Fourth Week 21 Aug to 25 August )
C Suma bhai - Create generic report API (20230807-001) | Milestone | 100% |  | Completed
Aeron - Holiday shift should not counted in the Process Schedule form. | Milestone | 100% |  | Completed
Prasad- When stock is taken in alternate unit and issue in alternate unit then validation occurred " available quantity is not updated properly. | Goal | 0% |  | InProcess Development
C suma bhai - write log for all forms. | Milestone | 100% |  | Completed
Company not able to create | Milestone | 100% |  | Completed
Esperer- After save document not set previous company name ,branch name,division name and cateory on all form. | Goal | 90% |  | Return
Additional Task Done Which is not Planned
Esperer-Improved the performance in the sales inquiry form. | Milestone | 100% |  | Completed
Fabtech - System showing error while retreiving one document. Day Report form problem. | Milestone | 100% |  | Completed
Aeron - Process scheculer same date will not consider in that form. | Goal | 30% |  | Return
SPRINT - 7(August Fourth Week 28 Aug to 1 September )
Aeron - Process scheculer same date will not consider in that form. | Goal | 30% |  | Return
Esperer- After save document not set previous company name ,branch name,division name and cateory on all fomr | Goal | 90% |  | Return
Prasad- When stock is taken in alternate unit and issue in alternate unit then validation occurred " available quantity is not updated properly. | Goal | 0% |  | InProcess Development
SANGIR PLASTICS PVT. LTD.-In Po Case Alternet Unit Use And Grn Delete That Time Pending Not Proper Update In Purchaseorderdetaiilstable | Goal | 0% |  | InProcess Development
When we create sales invoice through mobile app then search criterial is not working . | Goal | 0% |  | InProcess
Self - Returnable Receipt add quantity more than pending quantity and save document that time error message comes . | Goal | 0% |  | InProcess(Planned in the Next Version)
Aeron - In item master need to increase length of item name field for and alternate name move to right side. | Goal |  |  | Bug/Enhancement Pre Testing

## 7.5.11 Points
SrNo | TicketDescription | Status
1 | Highcool-Add multiple items add in forecast | Done
2 | Prasad-without selecting manufacturing indent check box and also system not validate and allow to save forecast document | Done
3 | Prasad-if forecast document save without selecting manufacturing indent check box then if we edit/amend same forecast document and select the manufacturing indent check box then system allow to select and save the document | Done
4 | Prasad - When we set authorization on purchase order cancellation category and do the pruchase order cancellation against po then system does not allow to edit/amend.cancel po document untill and unless its authorized. | Done
5 | C Suma bhai-Sales Invoice generate through Mobile App( Final point is pending salesinvoicefinancedetails and salesinvoice header table is wrong) | Done | 1
6 | C Suma bhai-Branch Receipt pending list comes and save in the system. | Done | 2
7 | Alps - When we do the Holiday setup for all the emplyee and If any Employee comes on holiday then while impoting data from SQL Present (P) should be applicable for that employe on respective holiday. | Done | 3 | check in | additional
8 | Prakash - when we are generate payroll conformation that time half day is not consider in present day . | Next Version |  |  | 1)Analysis reports list of reports service creation
9 | Prakash - Item Amount Calculate wrong in process receipt form | Next Version |  |  | 2)Document level reports list service creation
10 | Aeron - Holiday shift should not counted in the Process Schedule form. | In Process |  | next week | 3)Generic report pdf creation.
11 | Aeron - Process scheculer same date will not consider in that form. | In Process | 4 | testing
12 | PRASHANT [PRASAD]-When we are create GRN form select item and tick fill qty that time system take much more time | Done
13 | PRASHANT [PRASAD]-In GSTR1 cancelled document count some times show and some time not show in the document required TAB | Kaushal
14 | PRASHANT [PRASAD]-when we are import exel sheet in purchase indent form that time exel sheet duplication itemname validation . | Done
15 | PRASHANT [PRASAD]-When we cancelled E-Invoice from Einvoice Cancellation document Auto punch should be optional | Kaushal (August Second week 07 Aug to 11 August)
16 | PRASHANT [PRASAD]-When we create Einvoice data using create E-way bill that time transaction type wrong pass Ex.'Combition of 1 & 2' | Kaushal (August Second week 07 Aug to 11 August)
17 | PRASHANT [PRASAD]-when we configured tax masterid in the Export withoutpayment tab after save ticke removed automatically. | Done |  | next week
18 | BIO RED-when we are create godown issue >> add multiple item and save the document that time system is taking too much time for save the document | Done
19 | SANGIR PLASTICS PVT. LTD.-In Po Case Alternet Unit Use And Grn Delete That Time Pending Not Proper Update In Purchaseorderdetaiilstable | In Process
20 | 20230725-002 => Unable to generate Reports and not able to authorize document in FTCPL (Fabtech) | Done
21 | 20230725-001 => When one time generates the B2CS generates and then uploads perfectly but when the delete and uploading duplicate entry (IceMake) | Sprint -5(August Third week 14 Aug to 18 August)
22 | 20230731-001 => In material request of complaint inward/Complaint management rate column required and price should come from price list ( As our spare items are price listed) (Same rate should come in visit report & Change should be possible) (IceMake) | Sprint -5(August Third week 14 Aug to 18 August )
23 | AMD-TraceInformation table for all transaction forms transaction type tab account name data is not joined. | If possible then we will do otherwise we will consider next version
24 | ICE MAKE - 20220201-003 When we create godown issue based on the indent then form will be slow | Sprint -4 (August Second week 07 Aug to 11 August)
25 | Prasad- When stock is taken in alternate unit and issue in alternate unit then validation occurred " available quantity is not updated properly.
26 | Fabtech - System showing error while retreiving one document. Day Report form problem.

## ExeTestingPoints
SrNo | TicketDescription
1 | Highcool-Add multiple items add in forecast
2 | Prasad-without selecting manufacturing indent check box and also system not validate and allow to save forecast document
3 | Prasad-if forecast document save without selecting manufacturing indent check box then if we edit/amend same forecast document and select the manufacturing indent check box then system allow to select and save the document
4 | Prasad - When we set authorization on purchase order cancellation category and do the pruchase order cancellation against po then system does not allow to edit/amend.cancel po document untill and unless its authorized.
5 | PRASHANT [PRASAD]-when we are import exel sheet in purchase indent form that time exel sheet duplication itemname validation .
6 | PRASHANT [PRASAD]-when we configured tax masterid in the Export withoutpayment tab after save ticke removed automatically.
7 | Fabtech - System showing error while retreiving one document. Day Report form problem.

## Sheet2
PRIMA AUTOMATION | Grn Seen At Bank Payment After Grn Base Return | PRIMA AUTOMATION-Grn Seen At Bank Payment After Grn Base Return
BALARK | when we create mrp against mrp jobwork indent and select item that time error is showing please select at least one row for workorder | BALARK-when we create mrp against mrp jobwork indent and select item that time error is showing please select at least one row for workorder
PRASHANT [PRASAD] | When we are create GRN form select item and tick fill qty that time system take much more time | PRASHANT [PRASAD]-When we are create GRN form select item and tick fill qty that time system take much more time
PRASHANT [PRASAD] | In GSTR1 cancelled document count some times show and some time not show in the document required TAB | PRASHANT [PRASAD]-In GSTR1 cancelled document count some times show and some time not show in the document required TAB
PRASHANT [PRASAD] | when we are import exel sheet in purchase indent form that time exel sheet duplication itemname validation . | PRASHANT [PRASAD]-when we are import exel sheet in purchase indent form that time exel sheet duplication itemname validation .
PRASHANT [PRASAD] | when we configured tax masterid in the Export withoutpayment tab after save ticke removed automatically. | PRASHANT [PRASAD]-when we configured tax masterid in the Export withoutpayment tab after save ticke removed automatically.
PRASHANT [PRASAD] | When we cancelled E-Invoice from Einvoice Cancellation document Auto punch should be optional | PRASHANT [PRASAD]-When we cancelled E-Invoice from Einvoice Cancellation document Auto punch should be optional
PRASHANT [PRASAD] | When we create Einvoice data using create E-way bill that time transaction type wrong pass Ex.'Combition of 1 & 2' | PRASHANT [PRASAD]-When we create Einvoice data using create E-way bill that time transaction type wrong pass Ex.'Combition of 1 & 2'
PRASHANT [PRASAD] | when we configured tax masterid in the Export withoutpayment tab after save ticke removed automatically. | PRASHANT [PRASAD]-when we configured tax masterid in the Export withoutpayment tab after save ticke removed automatically.
SELF | ESPERER - Pending point of Reference Transaction form | SELF-ESPERER - Pending point of Reference Transaction form
PRASHANT [PRASAD] | when we are import exel sheet in purchase indent form that time exel sheet duplication itemname validation . | PRASHANT [PRASAD]-when we are import exel sheet in purchase indent form that time exel sheet duplication itemname validation .
BIO RED | when we are create godown issue >> add multiple item and save the document that time system is taking too much time for save the document | BIO RED-when we are create godown issue >> add multiple item and save the document that time system is taking too much time for save the document
SANGIR PLASTICS PVT. LTD. | In Po Case Alternet Unit Use And Grn Delete That Time Pending Not Proper Update In Purchaseorderdetaiilstable | SANGIR PLASTICS PVT. LTD.-In Po Case Alternet Unit Use And Grn Delete That Time Pending Not Proper Update In Purchaseorderdetaiilstable
20230725-001 => When one time generates the B2CS generates and then uploads perfectly but when the delete and uploading duplicate entry (IceMake)
20230725-002 => Unable to generate Reports and not able to authorize document in FTCPL (Fabtech)
24 | BALARK-when we create mrp against mrp jobwork indent and select item that time error is showing please select at least one row for workorder. | Next Version

## TestingWeeklyPlanning
Testing Team Planning
Team Leader | Rangani Vijay
Testing Executive | Kinjal Jani
Testing Executive | Yuraj
Testing Executive | Vivek
SPRINT - 6(August Fourth Week 21 Aug to 25 August )
Total Hours | 207 Hrs
Testing Team Planning
SrNo | Description | Remarks
1 | C Suma bhai - Create generic report API (20230807-001) | Completed
2 | Aeron - Holiday shift should not counted in the Process Schedule form. | Completed
3 | Prasad- When stock is taken in alternate unit and issue in alternate unit then validation occurred " available quantity is not updated properly. | InProcess Development
4 | C suma bhai - write log for all forms. | Completed
5 | Company not able to create | Completed
6 | Esperer- After save document not set previous company name ,branch name,division name and cateory on all form. | Return
Additional Task Done Which is not Planned
7 | Esperer-Improved the performance in the sales inquiry form. | Completed
8 | Fabtech - System showing error while retreiving one document. Day Report form problem. | Completed
9 | Aeron - Process scheculer same date will not consider in that form. | Return
7 | C suma bhai : Branch Receipt Generate through mobile app (20230713-001) | Approval Done
8 | When we do the holiday setup for all the employee and if any employee comes on holiday then while importing data from sql present should be applicable for that employee on respective holiday (20230324-004) | Approval Done
9 | C suma bhai : sales invoice generate through mobileapp | Approval Done
10 | Given the support to support team for the operational queries.
11 | Given the support to development team if they stuck some functional queries
12 | Meeeting with Kashif bhai and Kinjal for weekly planning.
13 | Training to our team members for better improvements.
14 | Solved the doubts of our team members.
15 | We planned daily for our daily tasks and check the queries.
16 | We will discuss with hetal sir regarding any bugs/enhancement relevant queries or functional changes.
17 | Esperer- After save document not set previous company name ,branch name,division name and cateory on all form.
SPRINT - 7(August Fourth Week 28 Aug to 01 September )
Total Hours | 144 Hrs
Testing Team Planning
SrNo | Description | Remarks
1 | Aeron - Process scheculer same date will not consider in that form. | Return
2 | Esperer- After save document not set previous company name ,branch name,division name and cateory on all fomr | Completed
3 | Prasad- When stock is taken in alternate unit and issue in alternate unit then validation occurred " available quantity is not updated properly. | InProcess Development
4 | SANGIR PLASTICS PVT. LTD.-In Po Case Alternet Unit Use And Grn Delete That Time Pending Not Proper Update In Purchaseorderdetaiilstable | Completed
5 | When we create sales invoice through mobile app then search criterial is not working . | Completed
6 | We will do the exe testing of the bugs which is we shown below : | Completed
7 | Given the support to support team for the client relevant queries.
8 | Given the support to our internal team if they stuck some coding relevant queries.
9 | Meeeting with Kashif bhai and Kinjal for weekly planning
10 | Training to our team members for better improvements.
11 | Solved the doubts of our team members.
12 | We planned daily for our daily tasks and check the queries.
13 | Given the support to testing team if they ask some queries.Either it will be return bug query or something else.
14 | Aeron - In item master need to increase length of item name field for and alternate name move to right side. | Completed
Additional Task Done Which is not Planned
1 | Self - Error message displays when select party name in fixed deposit receipt interest. | Completed
2 | Nimbus - When we are trying to edit/amend of sales invoice base return document then system is show validation message "Previous document is being amend after create this document " | Completed
EXE TESTING POINTS
SrNo | TicketDescription
1 | Highcool-Add multiple items add in forecast | Completed
2 | Prasad-without selecting manufacturing indent check box and also system not validate and allow to save forecast document | Completed
3 | Prasad-if forecast document save without selecting manufacturing indent check box then if we edit/amend same forecast document and select the manufacturing indent check box then system allow to select and save the document | Completed
4 | Prasad - When we set authorization on purchase order cancellation category and do the pruchase order cancellation against po then system does not allow to edit/amend.cancel po document untill and unless its authorized. | Completed
5 | PRASHANT [PRASAD]-when we are import exel sheet in purchase indent form that time exel sheet duplication itemname validation . | Completed
6 | PRASHANT [PRASAD]-when we configured tax masterid in the Export withoutpayment tab after save ticke removed automatically. | Completed
7 | Fabtech - System showing error while retreiving one document. Day Report form problem. | Completed
SPRINT - 8(04 September - 8 September )
Total Hours | 135 Hrs
Testing Team Planning
SrNo | Description | Remarks
1 | Aeron - Process scheculer same date will not consider in that form. | Return
2 | Exe Testing of Pending ALL Bugs | Completed | only pending exe testing of process schedule enhancement
3 | IceMake - parameter of party account masterid and batch no is not working in complain inward. | Completed
4 | Prasad - In returnable receipt issue based item code and item name is not sorting properly. | Completed
5 | C Suma bhai - We want to include document level discount coloumn in sales invoice mobile app. | Completed
6 | Senor - yearid not consider in udf formula in reference transaction. | Completed
7 | Senor - we need to open udf in sales followup at document level with following criteria dropdown, onthefly and need to insert query in result set. | Completed
8 | Create a Enhancment Note of Version 7.5.11
9 | Update a version in netpc and also check the version,create a company also.
10 | Given the support to development team regarding functional query, some doubt regarding bug / enhancement & case of bug. | 2.5 hours
11 | Meeeting with Kashif bhai and Kinjal for weekly planning | 1 hours
12 | Prepare Weekly planning sheet | 2 hours
13 | Solved the doubts of our team members regarding some functionality of bug / enhancement, functional query for test bug, discuss regarding defect case ect... | 2 hours
14 | We planned daily for our daily tasks and check the queries. | 4 hours
15 | Given the support to support / implemenation team if they ask some queries regarding functionality, bugs & enhancement ect... | 1.5 hours
Additional Task Done Which is not Planned
1 | Mehta - In drop down list master want to add nature under ProspectMaster | Completed
2 | C Suma bhai - Mobile App : Issue occurs while login in sales invoice. | Completed
3 | ESPERER :- Item Specification Functionality Not Work In Sales Inquiry Form. | Completed | PreTesting
4 | ESPERER :- Sales Inquiry >> In View Mode >> click on Terms And Condition Tab that time ERror Msg Display. | Completed | PreTesting
5 | ESPERER :- In Sales Inquiry Form UDF FieldType = Formula Not Work | Completed | PreTesting
6 | ESPERER :- In Sales Inquiry Form >> Edit Mode > Enter Details Description / Remark and click on ok button of ItemDetails that time error show. | Completed | PreTesting
7 | ESPERER :- Item Change Time Quantity Not Reset in Sales Inquiry Form. | Completed | PreTesting
SPRINT - 8(11 September - 15 September )
Total Hours | 180 Hrs
Testing Team Planning
SrNo | Description | Remarks
1 | Aeron - Process scheculer same date will not consider in that form. | Completed
2 | Exe Testing of Process schedule enhancement & new checking bugs | Completed
3 | Esperer - After save sales inquire document that time not set previous transaction currency. | Completed
4 | Mehta - prospect master nature field should be come in the drop down list master. | Completed
5 | Nimbus- In einvoice branch filter is not working other branch eninvoice is showing. | Not Come For Testing
6 | Nimbus - When we are trying to edit/amend of sales invoice base return document then system is show validation message "Previous document is being amend after create this document " | Not Come For Testing
7 | Balark - When we open process issue doc. No 16943 error come 'Data table internal index is currepted - 5' | Completed | PreTesting
8 | Balark - if godown issue receipt is done against more than one indent then edit, amend & delete button is hide when we retrive the document. | Completed | PreTesting
9 | RR kabel - Create new table for batch number, packing number generate new number from the effective date. | Pending | PreTesting
10 | RR kable - our main stock view conver from view to sp | Completed | PreTesting
11 | Create a Enhancment Note of Version 7.5.11 | Completed
12 | Update a version in netpc and also check the version,create a company also. | Completed
13 | Monthly KPI metting with niraj sir & Prepare KPI Sheet | 3 hours
14 | Given the support to development team regarding functional query, some doubt regarding bug / enhancement & case of bug. | 3 hours
15 | Meeeting with Kashif bhai and Kinjal for weekly planning & next version planning | 2.5 hours
16 | Weekly Functional Training | 4 hours
17 | Solved the doubts of our team members regarding some functionality of bug / enhancement, functional query for test bug, discuss regarding defect case ect... | 2 hours
18 | We planned daily for our daily tasks and check the queries. | 3 hours
19 | Given the support to support / implemenation team if they ask some queries regarding functionality, bugs & enhancement ect... | 1.5 hours
20 | Give Functional Training to developer | 4.5 hours
Additional Task Done Which is not Planned
1 | C Suma bhai - Mobile App : Issue occurs while login in sales invoice. | Completed
2 | ESPERER :- Item Specification Functionality Not Work In Sales Inquiry Form. | Completed | PreTesting
3 | ESPERER :- Sales Inquiry >> In View Mode >> click on Terms And Condition Tab that time ERror Msg Display. | Completed | PreTesting
4 | ESPERER :- In Sales Inquiry Form UDF FieldType = Formula Not Work | Completed | PreTesting
5 | ESPERER :- In Sales Inquiry Form >> Edit Mode > Enter Details Description / Remark and click on ok button of ItemDetails that time error show. | Completed | PreTesting
6 | ESPERER :- Item Change Time Quantity Not Reset in Sales Inquiry Form. | Completed | PreTesting
EXE TESTING POINTS
SrNo | TicketDescription
1 | Aeron - Process scheculer same date will not consider in that form. | Completed
2 | Ice Make - Multi-selection of Item Master in All Indent form. | Completed
3 | IceMake - parameter of party account masterid and batch no is not working in complain inward. | Completed
4 | Prasad - In returnable receipt issue based item code and item name is not sorting properly. | Completed
5 | Nimbus- In einvoice branch filter is not working other branch eninvoice is showing. | Completed
6 | Nimbus - When we are trying to edit/amend of sales invoice base return document then system is show validation message "Previous document is being amend after create this document " | Completed
7 | Mehta - prospect master nature field should be come in the drop down list master. | Completed
SPRINT - 1(19 September - 23 September )
Total Hours | 156 Hrs
Testing Team Planning
SrNo | Description | Remarks
1 | Balark - When we create process receipt and change batch no and go to another tab than after system will change batch no.... | Completed
2 | Kosambha - system dont carry forward udf data when both form have same udf name but field name is different. | Completed
3 | Esperer - After save sales inquire document that time not set previous transaction currency. | Return
4 | Esperer - Conversion Factor, Unit Quantity, Alternate Unit Quantity display wrong in sales quotation form. | Not Come For Testing
5 | Prakash - When we are going to do payroll confirmation then system does not calculate the salary properly (i.e. Salary calculation on 15 day in place of 18 days). | Not Come For Testing
6 | In Sales Invoice form >> copy transaction batch select >> refresh button click that time error show. | Completed
7 | Retrieve used unprocessreturn doc. that time delete button disable. | Return
8 | Nimbus : when we are generate e invoice that time branch name is showing company name | Not Come For Testing
9 | Ayushakti : Delete sales invoice time pending quantity update wrong in salesorderdetails table, | Not Come For Testing
10 | C suma bhai - write log for all forms with details entry. | Completed
11 | RR kabel - Create new table for batch number, packing number generate new number from the effective date. | Pending | PreTesting
Additional Task Done Which is not Planned
12 | Senor : In rate track when we select the check box of update master then system take too much time and time out error comes. | Completed
13 | Nimbus - When we are trying to edit/amend of sales invoice base return document then system is show validation message "Previous document is being amend after create this document " | Return
14 | Mehta : when we create sales invoice against visit report then open sales invoice base return form fill data and select item that time rate is showing zero in item details. | InProcess
15 | Balark : If Godown Issue Receipt is done against more than one indent then edit, amend, delete button is hide when we retrive the document again. | InProcess
16 | Icemake : when we edit or amend the product costing document and edit the rate or insert new item with rate and click on set button then net anount show zero value. | Completed | PreTesting
17 | Sales Invoice Base Return created against sales invoice that time delete button not disable in sales invoice form. | Completed | PreTesting
18 | Given the support to development team regarding functional query, some doubt regarding bug / enhancement & case of bug. | 2 hours & 45 minutes
19 | Meeeting with Kashif bhai and Kinjal for weekly planning | 1 hours & 15 minutes
20 | Prepare Weekly planning sheet | 1 hours & 15 minutes
21 | Solved the doubts of our team members regarding some functionality of bug / enhancement, functional query for test bug, discuss regarding defect case ect... | 2 hours & 30 minutes
22 | We planned daily for our daily tasks and check the queries. | 3 hours & 45 minutes
23 | Given the support to support / implemenation team if they ask some queries regarding functionality, bugs & enhancement ect... | 1 hours & 30 minutes
24 | Weekly Functional Training | 3.5 hours
25 | Give Functional Training to developer | 0 hours
SPRINT - 2(25 September - 29 September )
Total Hours | 180 Hrs
Testing Team Planning
SrNo | Description | Remarks
1 | Ice Make - Parameter of accountmasterid and batch no itemmasterid ,complain no,referenceid,is required to all tab of complain inward,complain management, visit report form. | Not Come For Testing
2 | Nimbus - When we are trying to edit/amend of sales invoice base return document then system is show validation message "Previous document is being amend after create this document " | Completed
3 | Self- Sales invoice base return created against sales invoice that time delete button disabled in sales invoice form | Completed
4 | Mehta : when we create sales invoice against visit report then open sales invoice base return form fill data and select item that time rate is showing zero in item details. | Completed
5 | Balark : If Godown Issue Receipt is done against more than one indent then edit, amend, delete button is hide when we retrive the document again. | Completed
6 | Prakash - When we are going to do payroll confirmation then system does not calculate the salary properly (i.e. Salary calculation on 15 day in place of 18 days). | Completed | PreTesting
7 | Nimbus : when we are generate e invoice that time branch name is showing company name | Completed
8 | Prasad - 20230801-001 When we issue for the raw material against any work order then also system shows the option ' Search Remove and Replace ' when we click on semi finish item in work order creation form . | Return
9 | RR kabel - Create new table for batch number, packing number generate new number from the effective date. | Completed | PreTesting
10 | Ice Make - Parameter of accountmasterid and batch no itemmasterid ,complain no,referenceid,is required to all tab of complain inward,complain management, visit report form. | Completed | PreTesting
11 | Bhagwati : Machine Disassmble i we transfer the assembly to another branch and system should track the original assembly unit. | Completed | PreTesting
Additional Task Done Which is not Planned
11 | Ice Make - when they create the costing entry the Net amount gets Zero when they click Item Process Rate then reflected (20230922-001 | InProcess
12 | Lonsen Kiri - Create a Service for the HDFC Bank utility. | Completed
13 | Nimus : When we are going to cancel invoice from ERP then in branch issue form Einvoice Cancel but new document no not generate | Completed
14 | Prepare Monthly KPI Sheet | 2 hours
15 | Given the support to development team regarding functional query, some doubt regarding bug / enhancement & case of bug. | 6 hours
16 | Meeeting with Kashif bhai and Kinjal for weekly planning | 1 hours 30 minutes
17 | Prepare Weekly planning sheet | 1 hours 30 minutes
18 | Solved the doubts of our team members regarding some functionality of bug / enhancement, functional query for test bug, discuss regarding defect case ect... | 3 hours 30 minutes
19 | We planned daily for our daily tasks and check the queries. | 2 hours 50 minutes
20 | Given the support to support / implemenation team if they ask some queries regarding functionality, bugs & enhancement ect... | 3 hours 10 minutes
21 | Weekly Functional Training | 3 hours
22 | Ask to developer regarding doubt in new develop functionality in bug / enhancement (HDFCAPI Configuration) | 6 hours
SPRINT - 3 (02 October - 6 October )
Total Hours | 180 Hrs
Testing Team Planning
SrNo | Description | Remarks
1 | Ice Make - Parameter of accountmasterid and batch no itemmasterid ,complain no,referenceid,is required to all tab of complain inward,complain management, visit report form. | Completed
2 | Prasad - 20230801-001 When we issue for the raw material against any work order then also system shows the option ' Search Remove and Replace ' when we click on semi finish item in work order creation form . | Completed
3 | Nimbus -Hi Support Team, We have generted a sales Supple Invoice from ERP. the system calculated wrong Tax value from ERP at the time of Einvoice generated. for your reference please find attached excel file. | Return
4 | Balark - Main Item Group parameter should be fetch in sub item group. Regards, Suresh Nakum 7016909264 ( Bug Id : 20230427-001) | Return
5 | Balark - Need filter for Equipment type and Group wise in Equipment tab in Process Master. | Return
6 | Prasad- When stock is taken in alternate unit and issue in alternate unit then validation occurred " available quantity is not updated properly. | Return
7 | Ice Make - when they create the costing entry the Net amount gets Zero when they click Item Process Rate then reflected (20230922-001 | Completed
8 | Atkotiya : - when we hide item master purchase tab, 3 options 1) packing size 2) rate per unit 3) rate per alternate unit then system is getting over lap with 2 option, | Completed
9 | Balark -Hello, When we open document no 16943 in process issue then attached error occurred. we want to delete this document. Regards, Suresh Nakum 7016909264 (20230906-006) | Completed
10 | Lonson kiri : Sales Order Cancellation Form Require Search Function | Completed | PreTesting
11 | Self : In Visit Report after add compalin no. & click on get data that time error message display | Completed | PreTesting
12 | Shree Bhagwati : in machine disassble we should do partial disassemble & add new part to the assembly. | Pending | PreTesting
Additional Task Done Which is not Planned
13 | Balark : System is not carry forwarding udf data when we make udf in replica's form. | Completed
14 | Madhav :- In Process Receipt form >> Required Auto Increase Batch no with +1. | InProcess
15 | Madhav :- In Process Receipt form >> WorkOrderId, WorkOrderRaisedId, WorkOrderRaisedDetailsId Required in Batch Details Grid. | Completed | PreTesting
16 | Balark :- In Consumption Master >> in Process >> in Process Plan Tab >> required multi selection in equipment group & equipment name. | Completed | PreTesting
17 | Mehta : - when we will create serialize number item's purchase invoice against grn that time system take too much time and get not-responding. | Completed | PreTesting
18 | Prima : - In FD Payment, when we clicko on finance effect tab then getting error 'Specified cast is not valid' | Completed | PreTesting
19 | Monthly KPI metting with niraj sir & Prepare KPI Sheet | 6 hours
20 | Given the support to development team regarding functional query, some doubt regarding bug / enhancement & case of bug. | 2 hours 30 minutes
21 | Meeeting with Kashif bhai and Kinjal for weekly planning | 45 minutes
22 | Prepare Weekly planning sheet | 1 hours 45 minutes
23 | Solved the doubts of our team members regarding some functionality of bug / enhancement, functional query for test bug, discuss regarding defect case ect... | 5 hours
24 | We planned daily for our daily tasks and check the queries. | 2 hours 45 minutes
25 | Given the support to support / implemenation team if they ask some queries regarding functionality, bugs & enhancement ect... | 1 hours 40 minutes
26 | Weekly Functional Training | 4 hours
27 | Meeeting with Kashif bhai and Kinjal for take bug/enhancement in version 7.5.12 | 1 hours
28 | Functional Discussion with sir. | 1 hours
SPRINT - 4 (09 October - 13 October )
Total Hours | 180 Hrs
Testing Team Planning
SrNo | Description | Remarks
1 | Nimbus -Hi Support Team, We have generted a sales Supple Invoice from ERP. the system calculated wrong Tax value from ERP at the time of Einvoice generated. for your reference please find attached excel file. | Completed
2 | Balark - Main Item Group parameter should be fetch in sub item group. Regards, Suresh Nakum 7016909264 ( Bug Id : 20230427-001) | Return
3 | Balark - Need filter for Equipment type and Group wise in Equipment tab in Process Master. | Completed | Testing Completed & Approval pending
4 | Prasad- When stock is taken in alternate unit and issue in alternate unit then validation occurred " available quantity is not updated properly. | Return
5 | Esperer - After save sales inquire document that time not set previous transaction currency. | Completed
6 | Madhav :- In Process Receipt form >> Required Auto Increase Batch no with +1. | Completed
7 | Madhav :- In Process Receipt form >> WorkOrderId, WorkOrderRaisedId, WorkOrderRaisedDetailsId Required in Batch Details Grid. | Completed
8 | Balark :- In Consumption Master >> in Process >> in Process Plan Tab >> required multi selection in equipment group & equipment name. | Not Come For Testing
9 | Prima : - In FD Payment, when we clicko on finance effect tab then getting error 'Specified cast is not valid' | Completed
10 | Esperer : Sales Inquiry >> In view mode >> click on terms and condition tab that time error msg display. | Not Come For Testing
11 | Esperer : Sales Inquiry >> Edit mode >> enter details description / remarks and click on oh button of itemdetails that time error show. | Completed
12 | Shree Bhagwati : in machine disassble we should do partial disassemble & add new part to the assembly. | Pending | PreTesting
Additional Task Done Which is not Planned
13 | Lonson kiri : Sales Order Cancellation Form Require Search Function | InProcess
14 | Esperer : In Sales Inquiry form UDF field type = formula not work | Completed | Testing Completed & Approval pending
15 | Esperer : Item Specification functionality not work in sales inquiry form. | Return
16 | Icemake : I have saved formula UDF in sales invoice grid and make it mandatory, when we amend the same document then do not consider validation and get error for HSN length. | Completed
17 | Prasad : In GRN form we are not able to hide or adjust the size of 'previous doc. pending quantity' column inGRN grid details grid. | Completed | PreTesting
18 | Given the support to development team regarding functional query, some doubt regarding bug / enhancement & case of bug. | 5 hours
19 | Meeeting with Kashif bhai and Kinjal for weekly planning | 40 minutes
20 | Prepare Weekly planning sheet | 1 hours 15 minutes
21 | Solved the doubts of our team members regarding some functionality of bug / enhancement, functional query for test bug, discuss regarding defect case ect... | 4 hours 30 minutes
22 | We planned daily for our daily tasks and check the queries. | 2 hours 30 minutes
23 | Given the support to support / implemenation team if they ask some queries regarding functionality, bugs & enhancement ect... | 2 hours
24 | Weekly Functional Training | 0 hours
25 | Ask to developer regarding doubt in new develop functionality in bug / enhancement. | 1 hours
SPRINT - 5 (16 October - 20 October )
Total Hours | 160 Hrs
Testing Team Planning
SrNo | Description | Remarks
1 | Exe-Testing of all bug for version 7.5.12
2 | Create a Enhancment Note of Version 7.5.12
3 | Update a version in netpc and also check the version,create a company also for version 7.5.12
4 | Balark - Main Item Group parameter should be fetch in sub item group. Regards, Suresh Nakum 7016909264 ( Bug Id : 20230427-001)
5 | Esperer : Item Specification functionality not work in sales inquiry form.
6 | Esperer : Sales Inquiry >> In view mode >> click on terms and condition tab that time error msg display.
7 | Aeron - In process scheduler when we double click on working hours that time system wrong time in plan end date time
8 | Self - In Visit Report after add complain no and click on get data that time error message comes.
9 | Lonson kiri : Sales Order Cancellation Form Require Search Function |  | Approval
10 | Balark - Need filter for Equipment type and Group wise in Equipment tab in Process Master.
11 | Balark : when we cancel the partial quantity of jobwork order and going to create jobwork issue then proporationate quantity of raw material is showing wrong. |  | PreTesting
12 | Given the support to development team regarding functional query, some doubt regarding bug / enhancement & case of bug.
13 | Meeeting with Kashif bhai and Kinjal for weekly planning
14 | Prepare Weekly planning sheet
15 | Solved the doubts of our team members regarding some functionality of bug / enhancement, functional query for test bug, discuss regarding defect case ect...
16 | We planned daily for our daily tasks and check the queries.
17 | Given the support to support / implemenation team if they ask some queries regarding functionality, bugs & enhancement ect...
18 | Weekly Functional Training
19 | Ask to developer regarding doubt in new develop functionality in bug / enhancement.